## cart e
Cart E
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
This month
Name | Due Date | Status | Dependency
Getting the Proposal Ready | 2023-09-30 | Working on it
Understanding and validating the previous design | 2023-10-15 | Working on it
Come up with a way to map more building | 2023-10-15 | Working on it
Improve Battery Life (vibration switch) | 2023-11-30 | Not Started
Map more buildings | 2023-11-30 | Not Started
Move the server to local | 2023-11-15 | Not Started
Working on studying the strength vs distance profile of wifi router we are using | 2023-11-15 | Not Started
Algorithms to use the past positions to avoid position jumps | 2023-12-30 | Not Started
Prototyping the new version using breadboard and testing | 2024-01-31 | Not Started
Getting the PCB for the new version ready (attempt 1) | 2024-02-29 | Not Started
Getting Multiple PCBs and make them work togeter | 2024-03-15 | Not Started
Getting the user interaction portal ready | 2024-03-31 | Not Started
Working on trianguation and accuracy improvement | 2024-05-15 | Not Started
2023-09-30 to 2024-05-15
New Group
Name | Due Date | Status | Dependency